## Submittals Schedule
SCHEDULE OF SUBMITTALS | [7 empty] | PROJECT # MXDP 23-5000 |  | PROJECT TITLE Renovate Silver Wings, B308 |  |  |  |  | SOLICITATION / CONTRACT NO.
(To be completed by Project Engineer) | [7 empty] | (To be completed by Contract Administrator)
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | C = Construction Project D = Design Project | LAUGHLIN DIV 01 SPECIFICATIONS | ENVIRONMENTAL QUALITY CONSTRUCTION SPECIFICATIONS LAFB | STATEMENT OF OBJECTIVES | NUMBER OF PAPER COPIES REQUIRED. DIGITAL COPIES ARE REQUIRED FOR ALL SUBMITTALS | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN SUSPENSE DATE | SUBMITTAL NUMBERS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL | REMARKS
[12 empty] | APPR | DIS
NTP 1 - Design
1 | Entry Access List (EAL) | D | 1.8.2 |  |  |  | 2 Weeks prior to base access
2 | Proof of OPSEC Training | D | 2.4 |  |  |  | 2 Weeks prior to base access
3 | Sive visit Agenda | D |  |  |  |  | within 7 Days after NTP 1
4 | Summary of site investigation | D |  |  |  |  | NLT 21 Days after NTP 1
5 | 15% Design Package | D |  |  |  |  | NLT 49 calendar days after NTP1
6 | 65% Design Package | D |  |  | 5.2.1 | 2 (drawings only) | NLT 42 calendar days after NTP1
7 | 95% Design Package | D |  |  | 5.2.2 | 2 (drawings only) | NLT 35 calendar days after Government approved 65% design submittal
8 | 100% Design Package | D |  |  | 5.2.3 | 2 (drawings only) | NLT 28 calendar days after Government approved 95% design submittal
9 | Progress Schedule Form and Contract Progress Report | C, D | 6.1.1 |  |  |  | Biweekly
10 | Meeting Minutes | D | 6.2.1 |  |  |  | NLT 3 Days after meeting
NTP 2 - Pre Construction
11 | Entry Access List (EAL) | C | 1.8.2 |  |  |  | 2 Weeks prior to base access
12 | Proof of OPSEC Training | C, D | 2.4 |  |  |  | 2 weeks prior to base access
13 | Contractor Safety Plan | C | 3.2.2 | 3.4.2.2 |  |  | NLT 30 days after NTP 2
14 | Certificate of Contractor Safety Compliance |  | 3.2.3 |  |  |  | NLT 7 days after NTP 2
15 | QC Manager Qualifications | C, D | 4.2.3 | 3.1.2 |  |  | NLT 7 days after NTP 2
16 | QC Plan | C, D | 4.2.4 |  |  |  | NLT 30 days after NTP 2
17 | Construction Site Plan |  | 12.1 |  |  |  | NLT 30 days after NTP 2
18 | Hazardous Material Approval (Safety Data Sheets) | C |  | 3.2.1 |  |  | NLT 30 days after NTP 2 (as required)
19 | Hazardous Waste Training Certificate |  |  | 3.2.2 |  |  | Prior to NTP 3 (as required)
20 | Hazardous Waste / Material Procedures |  |  | 3.2.2 |  |  | Prior to NTP 3 (as required)
21 | Public Water System Notification |  |  | 3.4.1 |  |  | NLT 30 days after NTP 2 (as required)
22 | Customer Service Inspection Certificate (TCEQ Form 20699) |  |  | 3.4.1 |  |  | Prior to NTP 3 (as required)
23 | TCEQ Public water system plan review submittal form (TCEQ Form 10233) |  |  | 3.4.1 |  |  | Prior to NTP 3 (as required)
24 | Clean Water Act TCEQ’s General Permit |  |  | 3.4.2 |  |  | Prior to NTP 3 (as required)
25 | Asbestos Hazard Abatement Plan |  |  | 3.5.2.1 |  |  | NLT 10 days prior to construction start
26 | Copy of notification to Department of State Health Services |  |  | 3.5.2.1 |  |  | NLT 10 days prior to construction start
27 | Worker/Area Protection Plan |  |  | 3.5.2.2 |  |  | Prior to NTP 3 (as required)
28 | Records of Existing Conditions | C, D | 1.5, 7.1.1 |  | 2.4 |  | NLT 30 Days after NTP 2
29 | Non-Hazardous Waste Disposal Manifest and/or Waste Shipment Record | C |  | 5.1 / 6.2 |  |  | NLT 45 days from the date of signature of receiving facility
30 | Submittals per Contractor's Design SOW | D | 10.4.4 through 10.4.11 |  |  |  | TBD
NTP 3 - Construction
31 | Hazardous Waste Disposal Manifests | C |  | 5.2 / 6.2 |  |  | As required, prior to removal from Government property
32 | Hazmat Usage Log | C |  | 6.1 |  |  | End of each month during construction
33 | QC Daily Inspection Reports | C | 4.2.6 |  |  |  | Weekly
34 | Progress Schedule Form and Contract Progress Report | C | 6.1 |  |  |  | Biweekly
35 | Meeting Minutes | C | 6.2.1 |  |  |  | NLT 3 Days after meeting
36 | Materials Testing | C | 7.1.3 |  |  |  | As required, within 7 days of test
37 | Operation and Maintenance Data | C | 10.4.12 |  |  |  | NLT 2 weeks after Final Inspection
38 | As Built Drawings/CAD Files | C | 10.4.13 |  |  | 2 (D size) | NLT 2 weeks after Final Inspection
39 | Completion Inspection (QC Manager Punchlist) | C | 13.4 |  |  |  | NLT 3 days after Pre-Final Inspection
40 | Draft DD Form 1354 | C | 13.3 |  |  |  | Prior to Pre-Final Inspection
41 | Final DD Form 1354 | C | 13.3 |  |  |  | At Final Inspection
42 | Construction Warranty Management Plan | C | 13.2 |  |  |  | NLT 2 weeks after Final Inspection
Schedule of Submittals Template, Feb 05 (SAF/AQCP)
Note on N7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on O7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)